## Budget
Document provided by the Project Manager and Task Managers
Task Name | Duration | Start | Finish | Resources |  |  |  |  | Total Budget (Hours and Cost)
Simple Project | 255 days | Mon 4/29/24 | Fri 4/18/25
Top Task 1 | 125 days | Mon 4/29/24 | Fri 10/18/24
Sub-Task 1.1 | 15 days | Mon 4/29/24 | Fri 5/17/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 100 | 60 | 0 | 0 | 0 | 160
|  |  |  | 10000 | 7200 | 0 | 0 | 0 | 17200
Sub-Task 1.2 | 30 days | Mon 5/20/24 | Fri 6/28/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 200 | 160 |  | 1 |  | 360
|  |  |  | 20000 | 19200 | 0 | 500 | 0 | 39700
Sub-Task 1.3 | 80 days | Mon 7/1/24 | Fri 10/18/24
Activity 1.3.1 | 60 days | Mon 7/1/24 | Fri 9/20/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 48 | 96 | 0 | 1 | 0 | 144
|  |  |  | 4800 | 11520 | 0 | 500 | 0 | 16820
Activity 1.3.2 | 20 days | Mon 9/23/24 | Fri 10/18/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 40 | 48 |  | 1 |  | 88
|  |  |  | 4000 | 5760 | 0 | 500 |  | 10260
Top Task 2 | 120 days | Mon 7/1/24 | Fri 12/13/24
Sub-Task 2.1 | 90 days | Mon 7/1/24 | Fri 11/1/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 240 |  |  | 1 |  | 240
|  |  |  | 24000 | 0 | 0 | 500 |  | 24500
Sub Task 2.2 | 30 days | Mon 11/4/24 | Fri 12/13/24 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 240 |  | 120 | 1 |  | 360
|  |  |  | 24000 | 0 | 10800 | 500 |  | 35300
Top Task 3 | 90 days | Mon 12/16/24 | Fri 4/18/25
Sub-Task 3.1 | 30 days | Mon 12/16/24 | Fri 1/24/25 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 180 | 120 | 90 | 1 |  | 390
|  |  |  | 18000 | 14400 | 8100 | 500 | 0 | 41000
Sub-Task 3.2 | 40 days | Mon 1/27/25 | Fri 3/21/25 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 120 | 84 | 120 | 1 | 1 | 324
|  |  |  | 12000 | 10080 | 10800 | 500 | 200 | 33580
Sub-Task 3.3 | 20 days | Mon 3/24/25 | Fri 4/18/25 | Designer | Engineer | Consultant | Software | Testing Software
|  |  |  | 100 | 120 | 90 | 500 | 200
|  |  |  | 60 | 0 | 72 | 0 | 1 | 132
|  |  |  | 6000 | 0 | 6480 | 0 | 200 | 12680
Project Duration | [8 empty] | 2198
Project Budget | [8 empty] | 231040

## Budget Distribution
Simple Project - Budgeted Cashflow
[6 empty] | Year | 2024 |  |  | 2025
Task Name | Work | Duration | Start | Finish |  | Quarter | Q2 | Q3 | Q4 | Q1 | Q2
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 4/18/25 | Distribution | 236460 | 56900 | 38348 | 66992 | 64864 | 9356
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 4/18/25 | Cummulative |  | 56900 | 95248 | 162240 | 227104 | 236460
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 10/18/24 | Distribution | 83980 | 56900 | 20248 | 6832
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 10/18/24 | Cummulative |  | 56900 | 77148 | 83980 | 83980 | 83980
Top Task 2 | 600 hrs | 120 days | Mon 7/1/24 | Fri 12/13/24 | Distribution | 60600 |  | 18100 | 42500
Top Task 2 | 600 hrs | 120 days | Mon 7/1/24 | Fri 12/13/24 | Cummulative |  |  | 18100 | 60600 | 60600 | 60600
Top Task 3 | 846 hrs | 90 days | Mon 12/16/24 | Fri 4/18/25 | Distribution | 91880 |  |  | 17660 | 64864 | 9356
Top Task 3 | 846 hrs | 90 days | Mon 12/16/24 | Fri 4/18/25 | Cummulative |  |  |  | 17660 | 82524 | 91880

## Actuals Data (06-28-2024)
Document provided by the Project Manager and Task Managers (Actuals Update on 06-28-2024)
Task Name | Duration | Start | Finish | Actual Start | Actual Finish | Actual Resources |  |  |  |  | Total Actual (Hours and Cost) | Remaining Resources |  |  |  |  | Total Actual (Hours and Cost) | EAC Hours
Simple Project | 255 days | Mon 4/29/24 | Fri 4/18/25 | Mon 4/29/24
Top Task 1 | 125 days | Mon 4/29/24 | Fri 10/18/24 | Mon 4/29/24
Sub-Task 1.1 | 15 days | Mon 4/29/24 | Fri 5/17/24 | Mon 4/29/24 | Fri 6/7/24 | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 120 | 72 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 192
[6 empty] | 12000 | 8640 | 0 | 0 | 0 | 20640 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Task 1.2 | 30 days | Mon 5/20/24 | Fri 6/28/24 | Wed 6/12/24 |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 0 | 500 | 0 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 24 | 32 |  | 0 |  | 56 | 180 | 128 |  | 1 |  | 308 | 364
[6 empty] | 2400 | 3840 | 0 | 0 | 0 | 6240 | 18000 | 15360 | 0 | 500 | 0 | 33860
Sub-Task 1.3 | 80 days | Mon 7/1/24 | Fri 10/18/24
Activity 1.3.1 | 60 days | Mon 7/1/24 | Fri 9/20/24 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 90 | 0 | 1 | 0 | 132 | 132
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 10800 | 0 | 500 | 0 | 15500
Activity 1.3.2 | 20 days | Mon 9/23/24 | Fri 10/18/24 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 | 0 |  | 0 |  | 0 | 40 | 48 |  | 1 |  | 88 | 88
[6 empty] | 0 | 0 | 0 | 0 |  | 0 | 4000 | 5760 | 0 | 500 |  | 10260
Top Task 2 | 120 days | Mon 7/1/24 | Fri 12/13/24
Sub-Task 2.1 | 90 days | Mon 7/1/24 | Fri 11/1/24 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 |  |  | 0 |  | 0 | 240 |  |  | 1 |  | 240 | 240
[6 empty] | 0 | 0 | 0 | 0 |  | 0 | 24000 | 0 | 0 | 500 |  | 24500
Sub Task 2.2 | 30 days | Mon 11/4/24 | Fri 12/13/24 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 |  | 0 | 0 |  | 0 | 240 |  | 120 | 1 |  | 360 | 360
[6 empty] | 0 | 0 | 0 | 0 |  | 0 | 24000 | 0 | 10800 | 500 |  | 35300
Top Task 3 | 90 days | Mon 12/16/24 | Fri 4/18/25
Sub-Task 3.1 | 30 days | Mon 12/16/24 | Fri 1/24/25 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 | 0 | 0 | 0 |  | 0 | 180 | 120 | 90 | 1 |  | 390 | 390
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 14400 | 8100 | 500 | 0 | 41000
Sub-Task 3.2 | 40 days | Mon 1/27/25 | Fri 3/21/25 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 84 | 120 | 1 | 1 | 324 | 324
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 10080 | 10800 | 500 | 200 | 33580
Sub-Task 3.3 | 20 days | Mon 3/24/25 | Fri 4/18/25 |  |  | Designer | Engineer | Consultant | Software | Testing Software |  | Designer | Engineer | Consultant | Software | Testing Software
[6 empty] | 100 | 120 | 90 | 500 | 200 |  | 100 | 120 | 90 | 500 | 200
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 72 | 0 | 1 | 132 | 132
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6480 | 0 | 200 | 12680
Project Duration | [10 empty] | 248 | [5 empty] | 1974 | 2222
Project Budget | [10 empty] | 26880 | [5 empty] | 206680
Task Name | Work | Duration | Start | Finish |  | Quarter | Q2 | Q3 | Q4 | Q1 | Q2
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 4/18/25 | Distribution | 236460 | 56900 | 38348 | 66992 | 64864 | 9356
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 4/18/25 | Cummulative | 236460 | 56900 | 95248 | 162240 | 227104 | 236460
Simple Project | 2262 | 265 | Mon 4/29/24 | Fri 5/2/25 | Actuals | 27380 | 27380 | 0 | 0 | 0 | 0
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 10/18/24 | Distribution | 83980 | 56900 | 20248 | 6832
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 10/18/24 | Cummulative | 83980 | 56900 | 77148 | 83980 | 83980 | 83980
| 816 | 134 | Mon 4/29/24 | Fri 11/1/24 | Actuals | 27380 | 27380
Top Task 2 | 600 hrs | 120 days | Mon 7/1/24 | Fri 12/13/24 | Distribution | 60600 |  | 18100 | 42500
Top Task 2 | 600 hrs | 120 days | Mon 7/1/24 | Fri 12/13/24 | Cummulative | 60600 |  | 18100 | 60600 | 60600 | 60600
| 0 | 0 | Mon 7/15/24 | Fri 12/27/24 | Actuals | 0
Top Task 3 | 846 hrs | 90 days | Mon 12/16/24 | Fri 4/18/25 | Distribution | 91880 |  |  | 17660 | 64864 | 9356
Top Task 3 | 846 hrs | 90 days | Mon 12/16/24 | Fri 4/18/25 | Cummulative | 91880 |  |  | 17660 | 82524 | 91880
Top Task 3 | 0 | 0 | Mon 12/30/24 | Fri 5/2/25 | Actuals | 0

## EAC (actuals till 06-28-2024)
Simple Project - Estimate At Completion (EAC) Cashflow
[6 empty] | Year | 2024 |  |  | 2025
Task Name | Work | Duration | Start | Finish |  | Quarter | Q2 | Q3 | Q4 | Q1 | Q2
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 5/2/25 | Distribution | 241100.01 | 42426.36 | 49478.98 | 60674.67 | 71590 | 16930
Simple Project | 2,198 hrs | 255 days | Mon 4/29/24 | Fri 5/2/25 | Cummulative | 241100 | 42426.36 | 91905.33 | 152580 | 224170 | 241100
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 11/1/24 | Distribution | 87820 | 42426.36 | 34045.64 | 11348
Top Task 1 | 752 hrs | 125 days | Mon 4/29/24 | Fri 11/1/24 | Cummulative | 87820 | 42426.36 | 76472 | 87820 | 87820 | 87820
Top Task 2 | 600 hrs | 120 days | Mon 7/15/24 | Fri 12/27/24 | Distribution | 61400 |  | 15433.33 | 45966.67
Top Task 2 | 600 hrs | 120 days | Mon 7/15/24 | Fri 12/27/24 | Cummulative | 61400 |  | 15433.33 | 61400 | 61400 | 61400
Top Task 3 | 846 hrs | 90 days | Mon 12/30/24 | Fri 5/2/25 | Distribution | 91880 |  |  | 3360 | 71590 | 16930
Top Task 3 | 846 hrs | 90 days | Mon 12/30/24 | Fri 5/2/25 | Cummulative | 91880 |  |  | 3360 | 74950 | 91880